## Webinar Timeline
Phase | Start Date | Week | Stages | Deliverables | Assigned Group | Due Date | Status | Addditioal Notes
Pre Webinar |  | 1 | Content and promotion creation | Webinar Script
Seed Questions
Speaker Bios
Presentation Slides
Presentation Video
Webinar Console Design
Determine interactive elements
Prepare any handouts our resources to be shared
|  | 2 | Promotion start/ Registration open | Webinar Registration Page
Email Copies
Social Media Promotional Graphics & Copy
Create promotional graphics
Develop Marketing Automation Campaign
Determine how we will ‘fill the seats’
Post-Webinar Survey
|  | 3 | Test Events | On24 Platform Testing
Conduct a test run with a select MarCom / Product Marketing / Speakers
Ensure a stable internet connection
Check audio and video equipment for clarity and functionality
Check audio and video equipment for clarity and functionality
Have Dematic Background
Pre-Record
|  | 4 | Final Updates | Finalize and upload any handouts or resources
Use On24's resource list feature to make them available for attendees
Webinar |  | WMS Webinar | During the webinar | Log in Early
Start the session 20-30 minutes early to address any technical issues
Title/Loading slide or countdown for those who join early (On24)
Greet attendees as they join and set the tone for the session
|  |  | Engage the audience | Make use of On24's interactive tools
Encourage attendees to participate and ask questions
|  |  | Content Delivery | Stick to the script but be flexible based on audience interactions
Maintain pacing and be mindful of the allocated time
Automated Captioning (On24)
Post Webinar |  | 1 | Follow Up | Determine follow-up strategy and process for complete attendee list with Business Development
Send out thank-you email to all attendees
Provide link to recording of webinar within 24-hours of event for those who missed live event
Provide a copy of the slides or other materials shared (if applicable)
Gather feedback using a post-webinar survey within 48-hours
Make sure there is a call to action. Whether it is, check out the Dematic website, sign up for future webinars, etc.
|  | 2 | Engage Non Attendees | Send 'we missed you’ emails copied with link to recording
|  | 3 | Analyze and Reflect | Use On24 analytics to gauge attendance, participation, and drop-off rates
Identify what worked well and areas for improvement in post-mortem with Dematic speakers / MarCom
Review leads generated and their quality
|  | 4 | Repurpose Webinar Content | Blog post: summarize key takeaways and link to recording
Insights article: Expand on topics covered in the webinar
Short videos: share clips from the webinar on social media
Put the webinar in a blog post or newsletter and promote it on social media platforms
Colomun A represents the different phases throughout the webinar
Colomun B and G represents the start and end date of the deliverables
Colomun C represents the weeks throughout the webinar
Coloumn D Represents the different kind of stages
Coloumn E is the list of deliverables that are set in place for webinars (Might be subjected to change)
Coloumn F represent which group is assigned to that specific deliverable
Coloumn H represents the current status of the deliverable. i.e In progress, completed,etc.